## Task Tracker
Task # | Subtask | Description | Deliverable | Assigned To | Status | Due Date | Notes
T1 |  | Ground Truth Analyses — Write expert reference analyses for each disruption scenario | Complete set of 10-12 reference analyses (see Scenarios sheet) |  | Not Started |  | Most critical task — LLM evaluation depends on this
T1 | 1.1 | Select 10-12 disruption scenarios from the Scenarios sheet (Task 3) | Finalized scenario list |  | Not Started |  | Coordinate with Task 3
T1 | 1.2 | For each scenario, classify the disruption: type, severity (1-10), estimated duration (weeks), affected supplier(s) | Classification table per scenario |  | Not Started |  | Use template on Ground Truth Template sheet
T1 | 1.3 | For each scenario, write a recommended allocation strategy with reasoning (2-3 paragraphs) | Strategy recommendation per scenario |  | Not Started |  | Explain WHY, not just what
T1 | 1.4 | For each scenario, list 3-5 risk factors a procurement manager should flag | Risk factor list per scenario |  | Not Started |  | Think: what could go wrong with the recommendation?
T1 | 1.5 | For each scenario, propose 2-3 concrete mitigation actions | Mitigation actions per scenario |  | Not Started |  | Actionable steps, not generic advice
T1 | 1.6 | Peer review — second team member reviews each ground truth for completeness and plausibility | Reviewed and finalized ground truth set |  | Not Started |  | Both reviewers sign off
T2 |  | Supplier Data Research — Research real-world titanium supplier parameters | Updated suppliers.csv with sourced data |  | Not Started |  | Makes the simulation credible for sponsor
T2 | 2.1 | Identify major global titanium sponge/bar stock producers (VSMPO-AVISMA, Timet, Toho, Baoji, etc.) | List of 6-8 real producers with region and products |  | Not Started |  | Sources: USGS, company websites, trade publications
T2 | 2.2 | Research approximate production capacities per producer (annual or weekly tonnage) | Capacity estimates with source citations |  | Not Started |  | Public data; exact numbers not required, ranges OK
T2 | 2.3 | Research typical lead times by region (US domestic, Japan, Russia, China, Australia) | Lead time table by region with justification |  | Not Started |  | Include shipping time, not just production
T2 | 2.4 | Research approximate market pricing for aerospace-grade titanium ($/kg or $/lb) | Price range table with sources and date |  | Not Started |  | USGS Mineral Commodity Summaries is a good start
T2 | 2.5 | Research aerospace qualification timelines — how long does supplier qualification take? | Summary paragraph with source |  | Not Started |  | Relevant to the qualified/not-qualified filter
T2 | 2.6 | Compile findings into an updated suppliers.csv with a companion justification document | Updated CSV + 1-2 page justification memo |  | Not Started |  | CSV format must match existing schema
T3 |  | Scenario Design — Create realistic disruption scenarios based on real events | 10-12 documented disruption scenarios |  | Not Started |  | These feed into Tasks 1 and 4
T3 | 3.1 | Research: 2022 Russian sanctions impact on titanium (VSMPO-AVISMA, Boeing/Airbus responses) | 1-page event summary with supply chain impact data |  | Not Started
T3 | 3.2 | Research: 2011 Japan earthquake/tsunami effect on specialty metals supply | 1-page event summary with supply chain impact data |  | Not Started
T3 | 3.3 | Research: COVID-19 logistics disruptions to metals supply chains (2020-2021) | 1-page event summary with supply chain impact data |  | Not Started |  | Focus on shipping delays and port closures
T3 | 3.4 | Research: China critical minerals export controls (recent or hypothetical) | 1-page event summary or plausible scenario write-up |  | Not Started |  | Can be a realistic hypothetical
T3 | 3.5 | Research: Factory fire or equipment failure at a titanium producer | 1-page event summary or plausible scenario write-up |  | Not Started |  | Timet or similar incidents
T3 | 3.6 | Design 3-4 additional scenarios: demand spike, quality failure, partial disruption, multi-supplier event | Scenario descriptions with parameters |  | Not Started |  | Vary severity and duration
T3 | 3.7 | For each scenario, define: disruption text (plain English input), expected duration, capacity impact %, affected supplier(s) | Completed scenario parameter table |  | Not Started |  | This becomes the test dataset
T4 |  | Evaluation Rubric — Define scoring criteria for LLM output quality | Rubric document with criteria and weights |  | Not Started |  | Complements automated BERTscore metrics
T4 | 4.1 | Define classification accuracy criteria: How close must type/severity/duration/supplier match the ground truth? | Classification scoring criteria (exact match, partial credit, thresholds) |  | Not Started |  | e.g., severity within +/- 1 = full credit
T4 | 4.2 | Define recommendation quality criteria: Does the LLM pick the right strategy? Is the reasoning sound? | Recommendation scoring criteria with examples of good/fair/poor |  | Not Started |  | Include examples at each quality level
T4 | 4.3 | Define risk assessment criteria: Are identified risks relevant? Complete? Actionable? | Risk assessment scoring criteria |  | Not Started
T4 | 4.4 | Define overall analysis quality criteria: Is the narrative clear, professional, free of hallucination? | Narrative quality scoring criteria |  | Not Started |  | Flag any fabricated facts as critical failure
T4 | 4.5 | Assign weights to each criterion (classification, recommendation, risk, narrative) totaling 100% | Weighted rubric table |  | Not Started |  | Discuss weights with advisor
T4 | 4.6 | Pilot test: Score 2-3 sample LLM outputs using the rubric to verify it is usable and discriminating | Pilot test results with any rubric revisions |  | Not Started |  | Advisor will provide sample LLM outputs
T5 |  | User Acceptance Testing — Test the Streamlit application and document findings | Testing log with findings and screenshots |  | Not Started |  | Run after advisor delivers updated app
T5 | 5.1 | Install and launch the application following the user manual instructions | Confirmation of successful install or documented issues |  | Not Started |  | Test on at least 2 different machines
T5 | 5.2 | Test Tab 1 (Full Pipeline) with each of the 4 built-in example scenarios | Screenshot + notes for each scenario run |  | Not Started |  | Note: classification correct? Strategies make sense?
T5 | 5.3 | Test Tab 1 with 3-4 custom disruption descriptions (from Task 3 scenarios) | Screenshot + notes for custom scenarios |  | Not Started |  | Test edge cases: vague input, multi-supplier, extreme severity
T5 | 5.4 | Test Tab 2 (Manual Scenario) with each supplier disrupted individually | Screenshot + notes for each manual test |  | Not Started |  | Try different durations and order quantities
T5 | 5.5 | Test Tab 3 (Supplier Database) — verify data displays correctly | Confirmation or issues noted |  | Not Started |  | Compare against suppliers.csv
T5 | 5.6 | Document any UI issues: confusing labels, missing information, layout problems, error messages | Prioritized issue list (critical/minor/cosmetic) |  | Not Started |  | Be specific — screenshot + description
T5 | 5.7 | Summarize: Would a procurement manager find this tool useful? What is missing for real-world use? | 1-page usability assessment |  | Not Started |  | Think from the Aerospace Corp sponsor perspective

## Ground Truth Template
Field | Instructions | Example (Russian Sanctions Scenario)
Scenario ID | Sequential number (S01, S02, ...) | S01
Scenario Title | Short descriptive name | Russian Sanctions on VSMPO-AVISMA
Disruption Description | Plain English description as a user would type it into the application (2-3 sentences) | New US/EU sanctions prohibit titanium purchases from Russian suppliers. VSMPO-AVISMA, the largest global titanium producer, is fully restricted. Existing contracts are suspended immediately.
Disruption Type | One of: GEOPOLITICAL, NATURAL_DISASTER, SUPPLIER_FAILURE, LOGISTICS_DELAY, DEMAND_SPIKE, QUALITY_ISSUE | GEOPOLITICAL
Severity (1-10) | 1 = minor delay, 10 = complete and permanent loss of supplier | 9
Estimated Duration (weeks) | How long the disruption is expected to last | 52 (indefinite; use 52 as proxy for 1+ year)
Affected Supplier(s) | Which supplier(s) in the database are impacted | Titan-RU
Capacity Impact % | Percentage of affected supplier capacity lost (0-100%) | 100%
Recommended Strategy | Which allocation strategy is best and why (2-3 paragraphs) | Proportional allocation among remaining qualified suppliers (Titan-US, Titan-JP, Titan-AU) is recommended. Titan-RU provided the lowest cost but highest lead time; losing 2,000 kg/week capacity is severe. Cheapest-first would overload Titan-JP (next cheapest), creating single-point-of-failure risk. Proportional spreads load and maintains supplier relationships for long-term stability, which matters in a 52-week disruption.
Risk Factors | 3-5 risks a procurement manager should consider (bulleted list) | 1. Remaining capacity (2,600 kg/wk qualified) may not meet demand 2. Titan-JP becomes concentration risk if proportional allocation overweights it 3. Titanium spot prices will spike globally 4. Qualification of Titan-CN as backup takes 12-18 months 5. Competitors will bid up same alternative suppliers
Mitigation Actions | 2-3 concrete steps to take | 1. Immediately negotiate increased allocation with Titan-AU and Titan-US 2. Begin qualification process for Titan-CN as contingency 3. Explore titanium recycling/scrap sources to supplement virgin supply
Source / Basis | Real-world event, published data, or expert judgment that informs this ground truth | Based on 2022 sanctions; Boeing initially continued purchasing, later reduced dependency. VSMPO-AVISMA supplies ~35% of Boeing titanium per Reuters reporting.

## Scenario List
ID | Title | Type | Severity | Duration (wks) | Affected Supplier | Capacity Impact % | Real Event? | Status
S01 | Russian sanctions (VSMPO-AVISMA) | GEOPOLITICAL | 9 | 52 | Titan-RU | 100% | Yes
S02 | Japan earthquake / tsunami | NATURAL_DISASTER | 7 | 12 | Titan-JP | 80% | Yes
S03 | COVID-19 shipping delays | LOGISTICS_DELAY | 5 | 16 | All | 30% | Yes
S04 | China export controls on titanium | GEOPOLITICAL | 8 | 26 | Titan-CN | 100% | Hypothetical
S05 | Factory fire at US producer | SUPPLIER_FAILURE | 6 | 8 | Titan-US | 100% | Plausible
S06 | Aerospace demand spike (new aircraft program) | DEMAND_SPIKE | 4 | 20 | None (demand +50%) | 0% | Plausible
S07 | Quality defect in Australian supply | QUALITY_ISSUE | 5 | 6 | Titan-AU | 100% | Plausible
S08 | Partial disruption — Russia capacity reduction | GEOPOLITICAL | 6 | 26 | Titan-RU | 60% | Plausible
S09 | Dual disruption — Japan earthquake + Russia sanctions | NATURAL_DISASTER + GEOPOLITICAL | 10 | 12 | Titan-RU, Titan-JP | 100% each | Plausible
S10 | No disruption (baseline) | NONE | 0 | 0 | None | 0% | N/A
S11 | (Student-defined scenario)
S12 | (Student-defined scenario)

## Evaluation Rubric Template
Criterion | Weight | Excellent (5) | Good (4) | Adequate (3) | Poor (2) | Failing (1)
Classification Accuracy | 25% | Type, severity, duration, and supplier all match ground truth | 3 of 4 fields match; severity within +/- 1 | 2 of 4 fields match | 1 field matches | No fields match or completely wrong type
Recommendation Quality | 30% | Correct strategy with sound, specific reasoning | Correct strategy with adequate reasoning | Reasonable strategy but weak reasoning | Suboptimal strategy or illogical reasoning | Harmful or nonsensical recommendation
Risk Identification | 20% | All key risks identified; actionable and specific | Most key risks identified | Some risks identified but generic | Few risks; mostly generic | Risks missing or irrelevant
Narrative Quality | 15% | Clear, professional, no hallucinated facts | Clear with minor issues | Understandable but disorganized or vague | Confusing or contains hallucinated claims | Incoherent or grossly inaccurate
Actionability | 10% | Mitigations are specific, feasible, and prioritized | Mitigations are reasonable | Mitigations are generic but relevant | Mitigations are vague | No useful mitigations